## Gantt
Lofthus Frukt & Saft Timeline |  |  | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6
Start date: 09/02-2020 |  |  | 2020-02-09 | 2020-02-10 | 2020-02-11 | 2020-02-12 | 2020-02-13 | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27 | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17
End date: 17/04-2020 |  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Task | Time | Assigned
PLANNING
Design/Layout Meeting w. Customer | 3 | FED / UX | bar: 2020-02-09 to 2020-02-11
Mockup build | 2 | UX | bar: 2020-02-12 to 2020-02-13
Design/Layout Review w. Customer | 2 | ALL | bar: 2020-03-16 to 2020-03-17
Design/Layout Approval w. Customer | 1 | ALL | bar: 2020-03-18
Server/Hosting | 3 | BED | bar: 2020-03-16 to 2020-03-18
DEVELOPMENT
Home page build | 2 | FED/UX | bar: 2020-03-19 to 2020-03-20
About page build | 2 | FED/UX | bar: 2020-03-23 to 2020-03-24
Product page build | 4 | FED/UX | bar: 2020-03-25 to 2020-03-30
Contact page build | 2 | FED/UX | bar: 2020-03-31 to 2020-04-01
Testing / Bugfixes | 4 | ALL | bar: 2020-03-27 to 2020-04-01
Re-testing and comfirmation | 2 | FED/UX | bar: 2020-04-02 to 2020-04-03
Article creation | 3 | CONT | bar: 2020-03-23 to 2020-03-25
Media content creation | 5 | PHOTO | bar: 2020-03-24 to 2020-03-31
PRE - DEPLOYMENT | 6
End user testing | 2 | FED/BED | bar: 2020-04-06 to 2020-04-07
Bug fixing | 2 | FED | bar: 2020-04-08 to 2020-04-09
Client testing w. customer | 1 | ALL | bar: 2020-04-10
Client approval w. customer | 1 | ALL | bar: 2020-04-13
DEPLOYMENT
Live deployment | 1 | BED | bar: 2020-04-14
Support | 2 | ALL | bar: 2020-04-15 to 2020-04-16
Project END | bar: 2020-04-17

## Teams
Team | Name | Shorthand
Fronte End Developer | Michael | FED
UX Designer | Chris | UX
Photography | Anne | PHOTO
Content | Liz | CONT
Back end | Dara | BED